## Items
High-level item | Pri | Team | Stakeholder | Size | Days | Date | Size | Days | Team | People | Start date
Must 1 | 1 | Team 1 | Stakeholder 1 | L | 30 | 2023-04-28 | S | 4 | Team 1 | 5 | 2023-04-22
Must 2 | 1 | Team 2 | Stakeholder 2 | M | 14 | 2023-04-27 | M | 14 | Team 2 | 3
Should 1 | 2 | Team 1 | Stakeholder 3 | S | 4 | 2023-04-29 | L | 30
Should 2 | 2 | Team 2 | Stakeholder 2 | XL | 90 | 2023-05-27 | XL | 90 |  | Subtract a person for on call as needed
Like to 1 | 3 | Team 1 | Team 1 | M | 14 | 2023-05-02
Date formula averages team effort, so each team's first few items have early dates
Formulas:
Date = Dates[Start date]+ROUNDUP(SUM(_xlws.FILTER(Items[Days],(Items[Team]=Items[[#This Row],[Team]])*(ROW(Items[Days])<=ROW(Items[[#This Row],[Days]]))))/XLOOKUP(Items[[#This Row],[Team]],Teams[Team],Teams[People]),0)